## Minor corrections
Page | Done | Examiner comment | Comment
11 | c | extra space after He*.
59 | c | Bad latex reference resulting in “??” partway down the page.
59 | c | line “…chapters ??..”
80 | c | Latex float issue(?) leading to a large space in the page.
84 | c | similarly, a large space here.
151 | c | “Connection to the experiment” should be emboldened (maybe just quote the section number).
192 | c | “…alternative approach presented in section 6.2.1”. It is section 6.2.1 | Latex error. The source code refs to the right section.
249 | c | Ref. [250], latex typo
250 | c | Ref. [351], typo “Optics COmmunications”; Ref. [353] formatting issues
0 | y | Page numbering starts on “0” instead of “1”, seems odd. | 0 is even
121 | n | The issue of the limitation of the dynamic range should be explained. Also the contradictory issues of SNR and saturation can be dealt with two different sets of measurements, right?
173 | y | figure shows power in mW, while the caption describes the powers in Watts. Would modify the figure axis to be consistent. | This seems unnecessary, the figure is perfectly legible.
197 | n | the significance of p-value should be stated.
0 | y | Spectrometry --- > spectrometry.
3 | y | Footnote 3, “Planck” not capitalised.
17 | y | “Hydrogen”, “Helium” written with caps, should be lowercase.
26 | y | footnote – “we consider -- Doubly” --> “we consider. Doubly…”.
28 | y | “coefficiencts” misspelled.
39 | y | typo in GPE, should be “i \hbar” on left, rather than “-\hbar”.
44 | y | “bell-type” --> “Bell-type”.
44 | y | “413nm” --> “413 nm”.
44 | y | line 5, “Bell-type” typo
45 | y | line 4, “ molecular pumps” (extra fullstop)
45 | y | line 5, fullstop missing
45 | y | line 10, “faraday” should be Faraday. There are several more instances of this typo in this chapter.
45 | y | line 13, LVIS should be defined.
50 | y | In the footnote the statement is a bit confusing as worded – it seems to imply that a collimated beam will converge to a focus. | No beam is perfectly collimated, and they will eventually come to a minimum waist then diverge. In any case, replaced with 'Technically speaking, the beam is not collimated in the same manner as a laser beam. The divergence is reduced, but not eliminated such that the spot size remains fixed or becomes focused'
51 | y | Eq. (2.2), the subscript “lab” should not be italicised.
53 | y | Missing space between number and unit in “2mm” and “1cm”.
58 | y | In the footnote, “analogoous” misspelled.
63 | y | “19.8eV” missing the space before the unit.
88 | y | “One of the most accessible lattice systems to realize with ultracold atoms is the Bose-Hubbard model.” – the wording is strange, just a typo(?) Bose-Hubbard is not a lattice system? Reword. | Replaced with 'One of the most accessible many-body systems to realize with ultracold bosons in an optical lattice is the Bose-Hubbard model.'
91 | y | “a.k.a.”
95 | y | “faraday” should be “Faraday”
95 | y | Is ETP the name of the manufacturer of the part? | The former, amended.
103 | y | “..1 0 ms delay ..” extra space in 10
104 | y | “Unforunately..”, second para, second line, typo
104 | y | “ NIM crate..” Is NIM defined? | Removed acronym and left only references to the system components
106 | y | First sentence: a larger range of momentum states does not necessarily mean a large phase space density. | Given a fixed atomic density, the statement is accurate, but I have amended to "Deeper optical dipole traps can contain more atoms at a given temperature by virtue of trapping over a larger range of particle momenta"
107 | y | “dipole fibers” is too colloquial. | "The dipole beams were first aligned to overlap with the magnetic trap by piping resonant light (at 1083 nm) through the dipole beam delivery fibres instead of 1550 nm."
119 | y | “…photon scattering signal…” what is it? | It's defined later in the sentence. Still, changed to "In both cases the effect of photon scattering manifests as a reduction of the total trapped final number $N$ relative to the final number $N_c$ in calibration shots."
121 | y | “..transduction from photon scattering to…”, the word “transduction” means something different. | I think this is fine, but have changed to "The functional relationship between photon scattering and atom loss via evaporative cooling is complicated and not linear."
126 | y | uK in Roman font
130 | y | The RF linewidth of the crystal oscillator of 300kHz sounds excessively large. | Fair assessment. It was actually in the RF driver output. I've added a sentence "In the first case, the linewidth is a result of frequency instability in the RF drive generation system. In the second, a newer drive system was in use which afforded better performance." It might be worth fixing this as it could affect in to the in-trap cooling performance.
134 | y | “section 5.3gives” missing a space
135 | y | “The tune-out frequency, where an atom does not interact with applied laser light…”. It is not true that at tune out frequency atoms do not interact with light, in fact, the imaginary part of the polarizability does not cancel at the tune out point. | Changed to 'The tune-out frequency, where an atom feels no force resulting from applied laser light, is an observable that tests QED independently of the conventional measurement of energy level differences.'
136 | y | “An equivalent model can be constructed using an LC circuit - the object of ultimate interest is the equation of motion,…” sounds very strange. | Relegated LC comment to footnote
167 | y | \chi^2/dof ~ 1 needs a space.
169 | y | “in Tab 5.2” inconsistent with later usage down the page, “table 5.2” and also elsewhere where “Tab. XX” is used. | I think the XX here is a placeholder by the examiner. I have changed both instances to read 'Tab.'
169 | y | “ 1140(20) MHz” should not italicized
171 | y | “also” twice..
181 | y | “smallest precision” to “highest precision”
194 | y | “especially” spelt wrong.
208 | y | Figure 6.8: From the text, it appears that these results are from the theory collaborators. They should be attributed in the figure caption.
224 | y | Ref. [18], “Bose-einstein”; Ref. [19] “structure of scince”
227 | y | Ref. [63], “evidence,” should be capitalised, “condesnation”
236 | y | Refs. [174, 175] duplicate.
237 | y | Refs. [187, 188] duplicate.
240 | y | Refs. [229, 230] duplicate. | Not duplicated, just very similar titles. Ref 229 is an experimental result, ref 230 is theory concerning the former.
241 | y | Ref [237] “87RbD-line” missing space.
134 | y | An energy level diagram would be apt to help follow the text. “Section 5.3 gives…” needs a space.

## Summary
Progress summary | [11 empty] | Review time | [5 empty] | Days/page
| Chapters | Title | Draft | Send to S | S reply | Send to A | A reply | Finish |  | Status key |  | Chapter | Title | S days | A days | Total | Pages | S | A | Total | pages/week
|  | Abstract |  | 2021-07-29 | 2021-08-13 | 2021-08-20 | 2021-08-23 | 2021-10-01 |  | 0 | Empty | Abstract | Abstract | 15 | 3 | 18 | 1 | 15 | 3 | 18 | 0.38889
| 0 | Overview |  | 2021-06-28 | 2021-07-01 | 2021-09-02 | 2021-09-15 | 2021-09-30 |  | 1 | Unstructured text/notes | 0 | Overview | 3 | 13 | 16 | 7 | 0.42857 | 1.8571 | 2.2857 | 3.0625
| 1 | Theoretical background |  | 2021-04-09 | 2021-04-22 | 2021-05-28 | 2021-06-21 | 2021-09-30 |  | 2 | Rough draft | 1 | Theoretical background | 13 | 24 | 37 | 14 | 0.92857 | 1.7143 | 2.6429 | 2.6486
| 2 | Experimental infrastructure |  | 2021-04-09 | 2021-04-22 | 2021-05-28 | 2021-06-21 | 2021-10-01 |  | 3 | Final proof | 2 | Experimental infrastructure | 13 | 24 | 37 | 20 | 0.65 | 1.2 | 1.85 | 3.7838
| 3 | Towards a lattice trap |  | 2021-07-06 | 2021-07-30 | 2021-09-04 | 2021-09-12 | 2021-10-01 |  | 4 | Done | 3 | Towards a lattice trap | 24 | 8 | 32 | 25 | 0.96 | 0.32 | 1.28 | 5.4688
| 4 | Transition measurements |  | 2021-07-06 | 2021-07-26 | 2021-09-02 |  | 2021-10-01 |  |  |  | 4 | Transition measurements | 20 | -44441 | -44421 | 11 | 1.8182 | -4040.0909 | -4038.2727 | -0.0017334
| 5 | Tuneout |  | 2021-09-10 | 2021-09-28 | 2021-09-29 |  |  | Review order switched |  |  | 5 | Tuneout | 18 | -44468 | -44450 | 32 | 0.5625 | -1389.625 | -1389.0625 | -0.0050394
| 6 | Quantum depletion |  | 2021-09-29 | 2021-10-06 |  |  |  | Review order switched |  |  | 6 | Quantum depletion | 7 |  |  | 29 | 0.24138
| 7 | Conclusion |  | 2021-09-14 | 2021-09-24 | 2021-09-27 | 2021-09-29 | 2021-09-29 |  |  |  | 7 | Conclusion |  |  |  | 4
[17 empty] | Average | 0.74179 | 1.2729 | 2.0146 | 3.7409
| Task list | [15 empty] | Median | 0.78929 | 1.4571 | 2.0679 | 3.4231
|  | Dates starting | 2021-07-26 | [14 empty] | Pages/day
|  | Chapter todo | Task | Time budget | Time spent | Next tasks | Time | Total time | [8 empty] | 1 | 0.066667 | 0.33333 | 0.055556
|  | Abstract | S revise | 1 |  | A revise | 0 | 1 | [8 empty] | 7 | 2.3333 | 0.53846 | 0.4375
|  | Overview | S revise | 0.5 |  | A revise | 1 | 1.5 | [8 empty] | 14 | 1.0769 | 0.58333 | 0.37838
|  | Theoretical background | A revise | 0.5 |  |  |  | 0.5 | [8 empty] | 20 | 1.5385 | 0.83333 | 0.54054
|  | Experimental infrastructure | A revise | 3 |  |  | 0 | 3 | [8 empty] | 25 | 1.0417 | 3.125 | 0.78125
|  | Towards a lattice trap | S revise | 5 |  | A revise | 2 | 7 | [8 empty] | 11 | 0.55
|  | Transition measurements | A revise | 1 |  | A revise | 1 | 2 | [8 empty] | 32
|  | Tuneout | Draft | 20 |  | A revise | 1 | 21 | [8 empty] | 29
|  | Quantum depletion | S revise | 2 |  | A revise | 2 | 4 | [8 empty] | 4
|  | Conclusion | S revise | 3 |  | A revise | 0.5 | 3.5 | [8 empty] | Average | 1.3481 | 0.78563 | 0.49637 | 0.26731
|  | Talk | Draft | 3 |  | Deliver | 1 | 4 | [8 empty] | Median | 1.267 | 0.68627 | 0.48359 | 0.29213
[7 empty] | Total w days | 47.5
[7 empty] | Total time | 66.5
| Countdown | Today's date | 2022-04-16 |  |  |  | Initial est. date | 2021-09-30 12:00
|  | Chapter | With? | Next task | Days on | Further tasks |  | Further time
| 0 | Abstract | Jake |  |  | Proof |  | 1 | <--Time budget for final proofread
| 1 | Overview | Jake |  | 0 | Proof
| 2 | Theoretical background | Jake |  |  | Proof
| 3 | Experimental infrastructure | Jake |  |  | Proof
| 4 | Towards a lattice trap | Jake |  | 0 | Proof
| 5 | Transition measurements | Jake |  | 0 | Proof
| 6 | Tuneout | Sean |  |  | Final revision |  | 2
| 7 | Quantum depletion | Sean |  | 0 | final comments |  | 1
| 8 | Conclusion | Jake |  | 0 |  |  | 0
|  | Talk | Jake |  | 0 |  |  | 0
[5 empty] | 0 |  |  | 4
[7 empty] | Total | 4
[7 empty] | Inc weekend | 5.6
[7 empty] | Running est. date | 2022-04-22
Formulas:
Finish = D15+[Finish, row above]
Finish = D29+ROUNDUP([Finish, row above],0)

## 2021
| Today's date | 2022-04-16 | Days to go
| Start date | 2021-01-26 |  |  |  | 445 | 356
| Draft target | 2021-05-18 | -333
| Submission target | 2021-06-15 | 140
Chapter | Title | Days on | Due | Revision time | Due | Weekends | Total days | Priority | Days til due | Status | Next
4 | Depletion | 5 | 2021-02-02 | 5 | 2021-05-24 | 2 | 7 | 1 | -438 | WIP | Finalize paper
2 | Background | 20 | 2021-03-31 | 5 | 2021-05-30 | 8 | 28 | 2 | -381
5 | Lattice | 15 | 2021-04-21 | 5 | 2021-06-05 | 6 | 21 | 3 | -360
1 | Introduction | 5 | 2021-04-28 | 3 | 2021-06-08 | 2 | 7 | 4 | -353
6 | Conclusion | 5 | 2021-05-05 | 2 | 2021-06-10 | 2 | 7 | 5 | -346
3 | Spectroscopy | 4 | 2021-05-09 | 3 | 2021-06-13 | 0 | 4 | 6 | -342 | Filled | Integrate, background, add TO/forbid?
0 | Abstract | 2 | 2021-05-11 | 2 | 2021-06-15 | 0 | 2 | 7 | -340
| Revision buffer | 5 | 2021-05-18 | 0 | 2021-06-15 | 2 | 7 | 8 | -333
Formulas:
Due = SINGLE(IF([Priority]<2,C2+[Total days],[Total days]+XLOOKUP([Priority]-1,I7:I14,D7:D14,0)))
Due = SINGLE(IF([Priority]<2,C3+ROUNDDOWN(1.2*[Revision time],0),ROUNDDOWN(1.2*[Revision time],0)+XLOOKUP([Priority]-1,I7:I14,F7:F14,0)))
Days til due = [Due]-TODAY()
Note on L7: jaker: NB: Originally made a 20-day weekend inclusive deadline for the jan 26. Now nudgeting days spent on revision before submission
Note on E11: jaker: Revision absorbed into Intro