## Summary
Progress summary | [11 empty] | Review time | [5 empty] | Days/page
| Chapters | Title | Draft | Send to S | S reply | Send to A | A reply | Finish |  | Status key |  | Chapter | Title | S days | A days | Total | Pages | S | A | Total | pages/week
|  | Abstract |  | 2021-07-29 | 2021-08-13 | 2021-08-20 | 2021-08-23 | 2021-10-01 |  | 0 | Empty | Abstract | Abstract | 15 | 3 | 18 | 1 | 15 | 3 | 18 | 0.38889
| 0 | Overview |  | 2021-06-28 | 2021-07-01 | 2021-09-02 | 2021-09-15 | 2021-09-30 |  | 1 | Unstructured text/notes | 0 | Overview | 3 | 13 | 16 | 7 | 0.42857 | 1.8571 | 2.2857 | 3.0625
| 1 | Theoretical background |  | 2021-04-09 | 2021-04-22 | 2021-05-28 | 2021-06-21 | 2021-09-30 |  | 2 | Rough draft | 1 | Theoretical background | 13 | 24 | 37 | 14 | 0.92857 | 1.7143 | 2.6429 | 2.6486
| 2 | Experimental infrastructure |  | 2021-04-09 | 2021-04-22 | 2021-05-28 | 2021-06-21 | 2021-10-01 |  | 3 | Final proof | 2 | Experimental infrastructure | 13 | 24 | 37 | 20 | 0.65 | 1.2 | 1.85 | 3.7838
| 3 | Towards a lattice trap |  | 2021-07-06 | 2021-07-30 | 2021-09-04 | 2021-09-12 | 2021-10-01 |  | 4 | Done | 3 | Towards a lattice trap | 24 | 8 | 32 | 25 | 0.96 | 0.32 | 1.28 | 5.4688
| 4 | Transition measurements |  | 2021-07-06 | 2021-07-26 | 2021-09-02 |  | 2021-10-01 |  |  |  | 4 | Transition measurements | 20 | -44441 | -44421 | 11 | 1.8182 | -4040.0909 | -4038.2727 | -0.0017334
| 5 | Tuneout |  | 2021-09-10 | 2021-09-28 | 2021-09-29 |  |  | Review order switched |  |  | 5 | Tuneout | 18 | -44468 | -44450 | 32 | 0.5625 | -1389.625 | -1389.0625 | -0.0050394
| 6 | Quantum depletion |  | 2021-09-29 | 2021-10-06 |  |  |  | Review order switched |  |  | 6 | Quantum depletion | 7 |  |  | 29 | 0.24138
| 7 | Conclusion |  | 2021-09-14 | 2021-09-24 | 2021-09-27 | 2021-09-29 | 2021-09-29 |  |  |  | 7 | Conclusion |  |  |  | 4
[17 empty] | Average | 0.74179 | 1.2729 | 2.0146 | 3.7409
| Task list | [15 empty] | Median | 0.78929 | 1.4571 | 2.0679 | 3.4231
|  | Dates starting | 2021-07-26 | [14 empty] | Pages/day
|  | Chapter todo | Task | Time budget | Time spent | Next tasks | Time | Total time | [8 empty] | 1 | 0.066667 | 0.33333 | 0.055556
|  | Abstract | S revise | 1 |  | A revise | 0 | 1 | [8 empty] | 7 | 2.3333 | 0.53846 | 0.4375
|  | Overview | S revise | 0.5 |  | A revise | 1 | 1.5 | [8 empty] | 14 | 1.0769 | 0.58333 | 0.37838
|  | Theoretical background | A revise | 0.5 |  |  |  | 0.5 | [8 empty] | 20 | 1.5385 | 0.83333 | 0.54054
|  | Experimental infrastructure | A revise | 3 |  |  | 0 | 3 | [8 empty] | 25 | 1.0417 | 3.125 | 0.78125
|  | Towards a lattice trap | S revise | 5 |  | A revise | 2 | 7 | [8 empty] | 11 | 0.55
|  | Transition measurements | A revise | 1 |  | A revise | 1 | 2 | [8 empty] | 32
|  | Tuneout | Draft | 20 |  | A revise | 1 | 21 | [8 empty] | 29
|  | Quantum depletion | S revise | 2 |  | A revise | 2 | 4 | [8 empty] | 4
|  | Conclusion | S revise | 3 |  | A revise | 0.5 | 3.5 | [8 empty] | Average | 1.3481 | 0.78563 | 0.49637 | 0.26731
|  | Talk | Draft | 3 |  | Deliver | 1 | 4 | [8 empty] | Median | 1.267 | 0.68627 | 0.48359 | 0.29213
[7 empty] | Total w days | 47.5
[7 empty] | Total time | 66.5
| Countdown | Today's date | 2022-06-19 |  |  |  | Initial est. date | 2021-09-30 12:00
|  | Chapter | With? | Next task | Days on | Further tasks |  | Further time
| 0 | Abstract | Jake |  |  | Proof |  | 1 | <--Time budget for final proofread
| 1 | Overview | Jake |  | 0 | Proof
| 2 | Theoretical background | Jake |  |  | Proof
| 3 | Experimental infrastructure | Jake |  |  | Proof
| 4 | Towards a lattice trap | Jake |  | 0 | Proof
| 5 | Transition measurements | Jake |  | 0 | Proof
| 6 | Tuneout | Sean |  |  | Final revision |  | 2
| 7 | Quantum depletion | Sean |  | 0 | final comments |  | 1
| 8 | Conclusion | Jake |  | 0 |  |  | 0
|  | Talk | Jake |  | 0 |  |  | 0
[5 empty] | 0 |  |  | 4
[7 empty] | Total | 4
[7 empty] | Inc weekend | 5.6
[7 empty] | Running est. date | 2022-06-25
Formulas:
Finish = D15+[Finish, row above]
Finish = D29+ROUNDUP([Finish, row above],0)

## 2021
| Today's date | 2022-06-19 | Days to go
| Start date | 2021-01-26 |  |  |  | 509 | 407.2
| Draft target | 2021-05-18 | -397
| Submission target | 2021-06-15 | 140
Chapter | Title | Days on | Due | Revision time | Due | Weekends | Total days | Priority | Days til due | Status | Next
4 | Depletion | 5 | 2021-02-02 | 5 | 2021-05-24 | 2 | 7 | 1 | -502 | WIP | Finalize paper
2 | Background | 20 | 2021-03-31 | 5 | 2021-05-30 | 8 | 28 | 2 | -445
5 | Lattice | 15 | 2021-04-21 | 5 | 2021-06-05 | 6 | 21 | 3 | -424
1 | Introduction | 5 | 2021-04-28 | 3 | 2021-06-08 | 2 | 7 | 4 | -417
6 | Conclusion | 5 | 2021-05-05 | 2 | 2021-06-10 | 2 | 7 | 5 | -410
3 | Spectroscopy | 4 | 2021-05-09 | 3 | 2021-06-13 | 0 | 4 | 6 | -406 | Filled | Integrate, background, add TO/forbid?
0 | Abstract | 2 | 2021-05-11 | 2 | 2021-06-15 | 0 | 2 | 7 | -404
| Revision buffer | 5 | 2021-05-18 | 0 | 2021-06-15 | 2 | 7 | 8 | -397
Formulas:
Due = SINGLE(IF([Priority]<2,C2+[Total days],[Total days]+XLOOKUP([Priority]-1,I7:I14,D7:D14,0)))
Due = SINGLE(IF([Priority]<2,C3+ROUNDDOWN(1.2*[Revision time],0),ROUNDDOWN(1.2*[Revision time],0)+XLOOKUP([Priority]-1,I7:I14,F7:F14,0)))
Days til due = [Due]-TODAY()
Note on L7: jaker: NB: Originally made a 20-day weekend inclusive deadline for the jan 26. Now nudgeting days spent on revision before submission
Note on E11: jaker: Revision absorbed into Intro