## 2021
| Today's date | 2021-06-09 | Days to go
| Start date | 2021-01-26 |  |  |  | 134 | 107.2
| Draft target | 2021-05-18 | -22
| Submission target | 2021-06-15 | 140
Chapter | Title | Days on | Due | Revision time | Due | Weekends | Total days | Priority | Days til due | Status | Next
4 | Depletion | 5 | 2021-02-02 | 5 | 2021-05-24 | 2 | 7 | 1 | -127 | WIP | Finalize paper
2 | Background | 20 | 2021-03-31 | 5 | 2021-05-30 | 8 | 28 | 2 | -70
5 | Lattice | 15 | 2021-04-21 | 5 | 2021-06-05 | 6 | 21 | 3 | -49
1 | Introduction | 5 | 2021-04-28 | 3 | 2021-06-08 | 2 | 7 | 4 | -42
6 | Conclusion | 5 | 2021-05-05 | 2 | 2021-06-10 | 2 | 7 | 5 | -35
3 | Spectroscopy | 4 | 2021-05-09 | 3 | 2021-06-13 | 0 | 4 | 6 | -31 | Filled | Integrate, background, add TO/forbid?
0 | Abstract | 2 | 2021-05-11 | 2 | 2021-06-15 | 0 | 2 | 7 | -29
| Revision buffer | 5 | 2021-05-18 | 0 | 2021-06-15 | 2 | 7 | 8 | -22
Formulas:
Due = SINGLE(IF([Priority]<2,C2+[Total days],[Total days]+XLOOKUP([Priority]-1,I7:I14,D7:D14,0)))
Due = SINGLE(IF([Priority]<2,C3+ROUNDDOWN(1.2*[Revision time],0),ROUNDDOWN(1.2*[Revision time],0)+XLOOKUP([Priority]-1,I7:I14,F7:F14,0)))
Days til due = [Due]-TODAY()
Note on L7: jaker: NB: Originally made a 20-day weekend inclusive deadline for the jan 26. Now nudgeting days spent on revision before submission
Note on E11: jaker: Revision absorbed into Intro

## Summary
Progress summary
Part | Chapter | Title | Draft | Send to S | S reply | Send to A | A reply | Finish |  | Status key
Intro | 1 | Overview | [7 empty] | 0 | Empty
| 2 | Theoretical background | [7 empty] | 1 | Unstructured text/notes
| 3 | Experimental infrastructure | [7 empty] | 2 | Stuctured notes
Metrology | 4 | Towards a lattice trap | [7 empty] | 3 | Final edits
| 5 | Transition measurements | [7 empty] | 4 | Done
| 6 | Tuneout | [8 empty] | June goal
Many-body | 7 | Quantum depletion | [8 empty] | June stretch goal
| 8 | Conclusion
Calendar
[8 empty] | M | T | W | Th | F | S | U
[8 empty] | 31 | 1 | 2 | 3 | 4 | 5 | 6
[8 empty] | 1: Mostly fig changes in apparatus; 2: MCP fig, laser cooling, TCP lock loop | Focus: | QD paper and apparatus
Gameplan |  |  |  | July goals |  |  |  | 1: Some minor text updates | DONE | QD paper -> Sean
Proceed using master June todo |  |  |  | Item | Target | Due
Check-off each task, count pomodoros on as estimate of time in |  |  |  | Overview | Draft | Week 5 |  | 7 | 8 | 9 | 10 | 11 | 12 | 13
Mark tasks done in calendar? |  |  |  | Apparatus | Send to A | Week 2 |  | 9: SENT CH2 | Focus: | Lattice & Apparatus chaps, half day on talk scoping
Adjust goals as learning along the way |  |  |  | Lattice | Send to S | Week 3 | [8 empty] | DONE | Apparatus -> Andrew
If ahead of goals on June 14th, consider booking talk |  |  |  | Transitions | Send to S&A | Week 4 | [8 empty] | Second goal:
|  |  |  | QD chap | send to S&A | Week 4 |  | 14 | 15 | 16 | 17 | 18 | 19 | 20
|  |  |  | QD paper | Resubmit | Week 1 | [8 empty] | Focus: | lattice & Main works chaps
|  |  |  | Conclusion | Send to S | Week 5 | [8 empty] | Due: | Lattice chapter -> Sean
|  |  |  | Extension | Submit | Week 5
[8 empty] | 21 | 22 | 23 | 24 | 25 | 26 | 27
[15 empty] | Focus: | Lattice & head/tail
|  |  |  | Reach goals | [10 empty] | Due: | main works chaps -> S & A
|  |  |  | Item | Target | Goal due
|  |  |  | Talk | Review | Week 2 |  | 28 | 29 | 30 | 1 | 2 | 3 | 4
[5 empty] | Practise | Week 4 | [8 empty] | Focus: | Details
[5 empty] | Deliver | Week 5 | [8 empty] | Due: | Intro/conclusion draft
|  |  |  | Tuneout chapter | Structured notes/pre-edit | Week 5

## Introduction
Section | Title | Section | Subsection | Status | Difficulty | Priority | Status key
1 | Theoretical background | Light and matter | Atomic structure | 2 |  |  | Empty | 0
1.1 |  |  | Interactions between atoms | 2 |  |  | References or brief points | 1
|  |  | Atoms and light | 0 |  |  | Referenced bullet points | 2
|  |  | Bose-Einstein condensation | 2 |  |  | Full sentences | 3
2 | Experimental infrastructure | Vacuum |  | 0 |  |  | Draft grade | 4
|  | Light sources | Spectroscopic laser | 0
|  |  | Master cooing laser | 0
|  |  | Optical distribution systems | 0
|  |  | Dipole trapping beams | 0
|  |  | Radio sources | 0
|  | Cooling and trapping atoms | Helium source | 0
|  |  | Optical molasses | 0
|  |  | Zeeman slower | 0
|  |  | MOTs | 0
|  |  | Magnetic traps | 0
|  |  | Evaporative cooling | 0
|  |  | Dipole traps | 0
|  | Detection modalites | Ion detection | 0
|  |  | Optical absorption imaging | 0
|  |  | MCP-DLD | 0
|  |  | Atom lasers | 0
|  | Data acquisition and control | Computer systems | 0
|  |  | Control software | 0
|  |  | Experimental sequences | 0

## Metrology
Chapter | Title | Section | Subsection | Status | Difficulty | Priority | Status key
| Section introduction | Atomic theory | Notation | 0 |  |  | 0 | Empty
|  |  | Dipole approx |  |  |  | 1 | First draft
|  |  | forbidden transitions |  |  |  | 2 | Proofread
|  | History of spectroscopy | Types of spectroscopy | 0 |  |  | 3 | Ready for feedback
|  |  | proton radius |  |  |  | 4 | Incorporating changes
3 | Transition measurements | Gap | Helium spectroscopy | 0 |  |  | 5 | Done
Vassen & Martin
|  | Aim & scope | Test limits of sensitivity & check Martin | 0 |  |  | Difficulty key (Max from each section)
|  | Contribution | Three methods, six lines | 0 |  |  | 1 | Dump and clean
|  |  | Direct A measurement |  |  |  | 2 | Revise past work
|  |  | QED seems fine |  |  |  | 3 | New work or reading
|  | Method: n=5 | Three-level theory & model | 0
Sequence
Analysis
|  | Methods: Forbidden | Theory & predicted SNR | 0
Sequences
Analysis
|  | Issues | Power & curvature measurements
instrumentation
Didn't actually test QED
|  | Next? | Isotope shifts & better reference
Different targets?
Link to next chapter
4 | Tuneout | Topic intro | Intuition: Classical oscillator | 0
Polarizability redux
Uses of Tuneouts
Previous measurement
|  | Gap | Have TO been used for QED? | 0
|  | Aim & scope | Measure the TO with sufficient precision to test QED | 0
|  | Contribution | We did it. | 0
|  | Method | Alignment | 0
Trap freq theory
|  |  | Fixed polz method | 0
Polarizability model
Fitting & determination
|  | Issues | Magnetic field pointing
Polarization issues
|  | Next? | Isotope shifts
| Chapter wrap | Key findings |  | 0
Section wrap
Link to next part

## ManyBody
Chapter | Title | Section | Subsection | Status | Difficulty | Priority | Status key
| Section introduction | Statistical physics | Laws of large numbers | 0 |  |  | 0 | Empty
|  | Phase transitions | Thermal, quantum, dynamical, computable, semantic | 0 |  |  | 1 | First draft
|  | Emergent complexity |  | 0 |  |  | 2 | Proofread
5 | Quantum depletion | Section intro | BEC detail | 0 |  |  | 3 | Ready for feedback
Bogoliubov theory
|  | Gap | Contact measurements | 0 |  |  | 4 | Incorporating changes
French disagreement
|  | Aim & scope | To reproduce the Palaiseau experiment | 0 |  |  | 5 | Done
|  | Contribution | They were wrong. TBD just how wrong. | 0
|  | Issues | Sys: Background | 0
Stat: Fitting power laws, weak signals
|  | Method | Sequence
Calibration stages
Processing
|  | What next? | Bragg spectroscopy? | 0
|  | Link to next chapter |  | 0
6 | Optical lattice | Section intro | Strong interactions | 0 |  |  | Difficulty key (Max from each section)
Simulation paradigms
|  |  | Implications for church turing? |  |  |  | 1 | Dump and clean
|  |  | State of optical lattices |  |  |  | 2 | Revise past work
|  | Gap | 1-body momentum measurements in optical lattices | 0 |  |  | 3 | New work or reading
|  | Aim & scope | To build the dang lattice | 0
|  | Contribution | Vacuum chamber | 0
Optics build inc dipole
Imaging
Sequence up to evap & dipole
Small simulations
|  | Progress meanwhile | New coils, solder catastrophe, new plates
|  | Issues/What next | Stability: Vibration, temp, vacuum | 0
Optics: Power, profile
Automatic optimization
7 | Conclusion | Revision of key findings |  | 0
|  | Biographical perspective |  | 0
|  | Outlook |  | 0
|  | Closing remarks |  | 0
| 7 | Conclusion | Revision of key findings | 0
|  |  | Biographical perspective | 0
|  |  | Outlook | 0
|  |  | Closing remarks | 0

## Wordcount
Dec | 13 | 4200
| 14 | 9250
| 15 | 16400